## Project plan
SAR In-Rapid-Time project plan |  |  | Sheila
SAR in Rapid Time Project Plan template [v2 17.04.23]
SCIE tools to support use of the SAR in Rapid Time model May 2023 See https://www.scie.org.uk/safeguarding/adults/reviews/in-rapid-time
MAPPING DATES AND TIME
|  |  |  | week 1 |  |  |  |  | CAPACITY ALLOCATION |  |  | week 1 |  |  |  |  | week 2 |  |  |  |  | week 3 |  |  |  |  | week 4 |  |  |  |  | week 5 |  |  |  |  | week 6 |  |  |  |  | week 7 | week 8
count of working days |  | Sheila QA | Lynn | 1 | 2 | 3 | 4 | 5 | BM | Reviewer 1 | Supervision/Reviewer 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
actual dates of days |  |  |  | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 |  |  |  | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-21 | 2023-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23
Reviewer 1 availability / non availability | [11 empty] | week 3 12: away; week 3 13: away; week 3 14: away; week 4 20: away; week 5 21: away
Reviewer 2 availabilty / non availability | bar: week 2 8; week 2 10; week 3 12 to week 3 14; week 4 17 to week 4 18; week 5 21; week 5 23
holidays or other dates to avoid
BM's PREPARATION AHEAD OF SET UP MEETING
Identify available SARiRT trained reviewer and SCIE support if needed
Confirm person and relevant family have been informed and who needs to be invited to contribute
Confirm agency record check returns are complete
Identify named leads from agencies involved to invite to Set Up meeting
Ask Agency Leads to identify named operational staff involved and if still employed
Identify local learning needs and areas to avoid duplicating learning from wider intelligence / strategic learning log
Check if all partners are signed up and understand how SARiRT is different and why
SET UP MEETING AND BM's FOLLOW-UP TASKS
Reviewers pre-reading of available record-checks (noting any key docs; and likely agency and operational participants)
Set Up Meeting with leads from involved agencies and reviewer(s) | Thurs. 24th Nov. 1 hour. Helen to select exact time between 11-2.00pm | 0.5 | 0.25 | bar: week 2 6
Send out write up of Set Up Meeting notes to all agency leads involved forming ToR; and other relevant people
Source any additional chronology and key records from involved agencies and share with reviewers in time for their Early Analysis Report drafting slot
Confirm all operational staff participants and agency leads on the basis of Set Up meeting decisions
Confirm all agency leads are clear as to their roles and responsibilities
Send out invites for all meetings in Project Plan [confirm dates and participants if holding invites sent out earlier]
BM check if any outstanding queries or concerns from participants
COLLABORATIVE, LEARNING-FOCUSED ANALYSIS
Drop in half hour for operational staff - introduction to approach and opp to meet the reviewers | Fri 25th Nov. 10am. Half an hour | bar: week 2 10
Reviewers draft Early analysis report (with SCIE support if needed) | Lynn draft KPEs ahead of Sheila/Lynn meeting on Mon 28th Nov 1-4pm | 0.5 | 1 | bar: week 3 11
Decide if sharing Early Analysis Report with operational staff participants
Structured Multi-Agency Workshop with operational participants | Lynn faciltiate case group workshop Tues 6th Dec or Wed 7th (preference 6th) 3 hours Helen to choose |  | 0.5 | bar: week 4 17 to week 4 18
Reviewer develops draft systems findings (with SCIE support if needed) | Lynn drafting systems findings ready for Sheila/Lynn meeting on 13th Dec 1-4pm | 0.5 | 0.5 | bar: week 4 17 to week 4 18; week 5 22
Meeting with involved agency leads to discuss and confirm systems findings (2hrs if poss) | Thurs 15th Dec. 2 hours Helen to specify |  | 0.25 | bar: week 5 24
Reviewer finalises systems findings report | Lynn to finalise report |  | 2 | bar: week 5 24
Regroup with operational workshop participants to share findings (1 hour check in to share findings) | Fri 16th Dec. 1 o'clock for 1 hour | bar: week 5 25
Report sign-off by involved Agency leads | bar: week 6 26 to week 6 27
0.25
|  | 1.5 | 4.75
CAPACITY TALLY
Total BM and reviewer capacity
KEY:
NO COLOUR - Business Managers activity
PINK - Reviewer activity
GREEN - involved agency leads activity
ORANGE - involved operational staff activity